“Innovators’ Breakfast”

EVENT PLANNER

This planner has been designed to guide you through the process of organising successful community-building events for companies and organisations connected through shared spaces, incubators, or networks. Whether you are planning a small networking meetup or a larger thematic event, this planner will help you stay organised, cover all key aspects, and ensure a smooth execution.

How to Use the Planner. The planner is structured around the key phases of event organisation - preparation, execution, and follow-up. Each section includes:

- Step-by-step checklists to guide your workflow

- Practical tips based on real-world experience

- Budget planning tips to track costs and identify funding sources

- Communication suggestions for effective coordination with speakers, attendees, and partners.

You can use this planner either sequentially or jump to specific sections depending on your needs. For best results, we recommend reviewing the full planner during your initial planning phase.

Real-World Insights. All examples and templates provided throughout this planner are based on a previously organised and successful event. These serve as concrete references to help you understand what works in practice and how to adapt the approach to your own context.

| CONCEPT OF THE EVENT |  |  |
| --- | --- | --- |
| This kind of event aims at connecting large corporations with start-ups where corporations reveal their processes to find solutions, develop new processes as well as utilize new technologies and applications. Innovative SMEs, start-ups, and spin-offs present their ideas and solutions to meet the challenges. Sometimes it is the other way around – start-ups present the solutions that they are working on and corporations decide if they can use/adapt them or not. Companies by themselves or with the help of organizers, organize follow-up meetings to establish purposeful partnerships and discuss investment opportunities. As an option, the event can also include a key presenter of the topic to start the event by presenting the context of the challenge, overview the tendencies in the field. Depending on the number of participants/challenges, the agenda can be different. If there is one corporation present, there is no need to create separate breakout rooms – SMEs, start-ups and spin-off can each present their ideas directly during the event. If organizers managed to find several corporations or one corporation has several challenges, it is advisable to create separate breakout rooms for each challenge. The event lasts for approximately 1-1,5 hours. |  |  |
| Task | Details | Responsible person / status |
| PREPARATORY STAGE |  |  |
| Topic/Theme of the event | Identify key topics for the event and/or survey the participants – corporations and SMEs/ start-ups/spin-offs. Start by identifying the corporation with a challenge and then try to match with suitable SMEs/start-ups/spin-offs. If you know an SME/start-up/spin-off with a good solution you can start with that and try to invite a corporation potentially interested in that solution. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Define your target group | The target group for this type of event is corporations, SMEs, start-ups, spin-offs. Think who could benefit from the event. Where are you going to disseminate information about it? | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Budget of the Event | Think of the sources of payments. Costs may include the following budget lines: Costs for Moderator Cost for Speaker Dissemination costs Organizational costs ---------------------------------------------- Total budget: | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Key speaker (if any) | Select the key Speaker. Focus on entrepreneurs, start-ups, researchers, and large corporations in the sector. Select speakers who are industry leaders, innovators, and successful entrepreneurs. Key presenter should start the event by presenting the context of the challenge, overview the tendencies in the field. Check if they are available and in the scope of your budget. During the planning stage you can share this file with all people involved in organizing the event and use this cell to brainstorm all possible options and then decide which candidate is the most suitable. The person assigned to this task should be responsible for contacting the Speaker, checking their availability, confirming payment details, and taking on all further communications with the Speaker. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Moderator of the event | A well-managed event depends on an experienced moderator who can steer the agenda, maintain engagement, and address any unforeseen challenges. It could be someone from your organization or outside. During the planning stage you can share this file with all people involved in organizing the event and to use this cell to brainstorm all possible options and then decide which candidate is the most suitable. If the moderator is from outside, the person assigned to this task should be responsible for contacting the potential Moderator, checking their availability, confirming payment details, and taking on all further communications with the Moderator. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Communication with participants | It is really important to clearly communicate with participants and moderator about what you expect from them and give them as many details about the challenge as you can. Have a pre-meeting with the corporation to get as much relevant information as you can. This will ensure a smooth and productive event that everyone would benefit from. Letters when communicating with participants should include: - Information about the event (challenge of the corporation, agenda) - Login link - Information about the key speaker (if you have one). This might draw more attention to your event and attract relevant participants. - Information about the corporation selected for the event and its’ challenge. Maybe some initial data that could be useful to know beforehand for the solution providers. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Link for participants' registration | For participants registration use Microsoft Forms or Google Forms. During this process it is important to gather all relevant information about the participants, so the questions should be well thought out. As in this type of the event, the participants are preselected, the actual registration form if a formality and will be only used to invite them to the event. Example of the registration form can be found in Annex No 1. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Automatic reply e-mail to the ones who registered: | Example message can be found in Annex No 2. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Agenda and Scenario | After finalising the event agenda, take your time to prepare a scenario for the event. This helps to play out all the event in advance and see in perspective what is ready and what is not. Example of information about the event online can be found in Annex No. 3. Example of the Scenario can be found in Annex No 4. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Breakout rooms (if any) | Depending on the number of participants/challenges, the agenda can be different. If there is one corporation present, there is no need to create separate breakout rooms – SMEs, start-ups and spin-off can each present their ideas directly during the event. If organizers managed to find several corporations or one corporation has several challenges, it is advisable to create separate breakout rooms for each challenge. A slide with brief challenge information is prepared in advance and shared in each room. Each room should have a moderator who would be briefed on their role in the breakout room before the event. Be mindful when setting the time for discussion so that it would be enough for presenting the solution and at least a small discussion between the corporation and the solution provider. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Create an Event link on Social networks (optional) | Example of a LinkedIn event can be found in Annex No 5. If the event is organized for a close group of participants a simple Calendar invite with all relevant information could be enough. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Dissemination | Prepare a visual for your event dissemination. Create a good title/ slogan/logo/colour scheme. Create visuals for PowerPoint presentations, and online event backgrounds for organizers to make your event look cohesive. For this type of events, the dissemination is mainly to be done by personal contacts, because organizers need to know corporations that have challenges and on the other hand SMEs/Start-ups/Spin-offs that could match them. Organizers can utilize the knowledge and contacts of other business support organizations and also can directly contact Universities or Research centers. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Information to the Moderator | Provide the moderator with all relevant information. Have a short description of the challenge(s) and solutions to share with the moderator. Share the scenario or share all relevant information for him/her to prepare the scenario by themselves. Share or discuss possible questions to the speakers, participants during discussions. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Remainder e-mails to participant few days before the Event | Example of an e-mail can be found in Annex No 6. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| EXECUTION OF THE EVENT |  |  |
| Reminder letter on the day of the Event | Example of an e-mail can be found in Annex No 7. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Start of the Event | Make sure all guests – speaker (if any), challenge owner and solution providers - are connected to the event. Connect 10-15 minutes prior the start of event to make a test slide shares, check microphones and cameras, and check roles and rights assigned to participants. Prepare and check the readiness of interactive elements like Q&A sessions, polls, and breakout rooms. Have a dedicated person responsible for technical management. Provide guidelines for respectful and constructive interactions. Ask participants to use chat for questions, remarks, sharing of contacts. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Event recording (optional) | Save and edit the recording and prepare a link to the video to be sent to the participants. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Follow the scenario but be flexible | Example of the Scenario can be found in Annex No 4. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Breakout rooms (optional) | Assign a person who will create and manage the breakout rooms. This should be the person who created the event link. If you have never delt with creating a breakout room before – make sure you make a test event with your colleagues to understand the specifics. You can assign participants to the breakout rooms only during the event. If there is one corporation present, there is no need to create separate breakout rooms – SMEs, start-ups and spin-off can each present their ideas directly during the event. If organizers managed to find several corporations or one corporation has several challenges, it is advisable to create separate breakout rooms for each challenge. In this case, assign a room moderator to lead work there. Have a Miro board or PowerPoint slide(s) with the written information about the challenge to facilitate discussions and to provide the possibility to create notes. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| POST-EVENT ACTIVITIES |  |  |
| Payments | If you had a paid moderator or guest speaker, check if all agreements are prepared, and invoices are issued correctly. Make transfers. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Follow-up letter to participants and request to fill in the satisfaction survey | Example of the follow-up letter to the participants can be found in Annex No 8. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |
| Follow-up meetings | Encourage participants to organize follow-up meetings to explore partnerships and investment opportunities. Contact the challenge owner to hear their insights after the event, did any of the solutions provided match the challenge, and which of the solution providers would they like to meet again and have further discussions. Provide a platform or channel for participants to schedule these meetings. | Click to enter person(s) assigned to this task Click to select the deadline for the task ☐not started ☐in progress ☐done |

ANNEX OF EXAMPLES

| No 1. Example of the registration form | Innovation Dialogues. How to co-create with corporations? The private and business sectors face a wide range of challenges: from process management in the health system and social welfare, to applying innovative tools in manufacturing and data protection. 📢Join us online for the event 🟠Innovation Dialogues. How to co-create with corporations? and find opportunities to face those challenges and develop innovations together with Lithuanian, Norwegian, and Latvian companies. This event offers a chance to network and connect with like-minded professionals across the Baltic Sea Region, get acquainted with the offers and talk about cooperation opportunities with representatives of corporations. If you are an innovation-open changemaker - this event is just for you! ➡️Key topis: #Agrotech solutions #AI tools for data management #Greentech for sustainable lifestyle WHEN ¦ June 3, 10:00 – 11:30 EET WHERE ¦ Online via TEAMS The link to the event will be sent after the registration. We collect your personal data for the following purposes: events, seminars, webinars, live trainings, hackathons, consultations, etc. organization; when you participate in our event, we may take screenshots, photos, video from ongoing event, we later may use it for our communication and gathering evidence for European Union funds reporting; when we meet in person, we may process data to implement COVID-19 prevention and control measures. More detailed information about the scope of personal data processing, purposes, means, your rights, etc.: https://www.techpark.lt/privacy-notice . 1.Your organization Text 2.Name, Surname Text 3.Your email Text |
| --- | --- |
| No 2. Example of the automatic reply for registered participants | Thank you for registering for Innovation Dialogues. How to co-create with corporations? event! 🗓️Join us on June 3, 10:00-11:30 EET 🔗Link to the event: enter link to the Event |
| No 3. Example of an information about the event and Agenda | The private and business sectors face a wide range of challenges: from process management in the health system and social welfare, to applying innovative tools in manufacturing and data protection. Join us online for the event Innovation Dialogues. How to co-create with corporations? and find opportunities to face those challenges and develop innovations together with Lithuanian, Norwegian, and Latvian companies. This event offers a chance to network and connect with like-minded professionals across the Baltic Sea Region, get acquainted with the offers and talk about cooperation opportunities with representatives of corporations. If you are an innovation-open changemaker - this event is just for you! Key topics: #Agrotech solutions #AI tools for data management #Greentech for sustainable lifestyle WHEN ¦ June 3, 10:00 – 11:30 EET WHERE ¦ Online via TEAMS. Register: https://forms.office.com/e/pPiHH45MaD // AGENDA (CEST) // 10:00-10:05 ¦ Welcome 10:05-10:45 ¦ Introduction of the companies, clusters and corporations: The head of AgriFood Lithuania DIH Speaker 1 will join the event to define the value of collaboration and partnerships in agro sector. Biotechnology company Brando is looking for #AI based agrotech chatbot. Experienced business developer, agri-biotech expert and the Head of Innovation at Brando Speaker 2 will help you explore the co-creation process. Brando invites you to develop a personalized virtual assistant (bot) for customer service and recommendation, able to process the company's data and apply LLM models to communicate with customers. 10:45-11:05 ¦ Startups introduce their solutions 11:05-11:20 ¦ Networking activities 11:20-11:30 ¦ Wrap-up |
| No 4. Example of the Scenario | Connecting: 10:45 ¦ Person from organizers receives participants. 10:00 - 10:10 ¦ Moderator: welcome, introduction, a brief history of such events, where the inspiration came from. What success stories we have: concrete examples. What is the specific theme of this event, what is the duration, summary of the programme, who are the participants, what is the objective. Mentions that participants are welcome to share contacts throughout the event, and after the event, organizers will share a joint letter. By organizing this international event our aim is to connect innovators across borders and foster collaboration among SMEs, startups, other developers, and various organizations. Moderator: brief justification for inviting Speaker 1. The rationale could be that Brando is a Biotech company and AgriFood is an innovative cluster that brings together researchers and other experts in the field, so their insights in agro should be useful for both Brando and the solution providers to make the best use of the solutions to their advantage. A word about AgriFood Lithuania. AgriFood Lithuania is a Digital Innovation Hub and Cluster that brings together major research, business and public stakeholders in Lithuania for the common pursuit of digital transformations in the agriculture, food and associated sectors. Invitation to start a 15 min presentation. 10:10 - 10:25 ¦ The head of AgriFood Lithuania DIH Speaker 1 - The value of collaboration and partnerships in agro sector. Moderator: thanks Speaker 1. Two-sentence reflection on what was most interesting/important. Invites participants to ask questions, if any. Moderator: Announces that the most important part of the event is now about to start - the presentation of the company and the challenge it has. Biotechnology company Brando invites you to develop a personalised virtual assistant (bot) for customer service and recommendation, able to process the company's data and apply LLM models to communicate with customers. Experienced business developer, agri-biotech expert and the Head of Innovation at Brando Speaker 2 will help you explore the co-creation process. Encourages participants to listen carefully so that their answers are as relevant as possible to the challenge at Brando. 10:25 - 10:40 ¦ Biotechnology company Brando representative Speaker 2 Moderator: thanks the participants, reflects on the main issue of the challenge. Maybe asks the audience if there are any questions, but stresses that there will be time for questions and answers after all the solution providers have spoken. Says that the challenge owner would be listening carefully now. 10:40 - 11:05 Moderator: says that there are 5 potential challenge solution providers present. Announces the order in which they will speak. Invites the first one, tells him that he has 5 minutes. After his/her speech, thank him/her and invite the next one, etc. 10:40 - 11:05 ¦ Startups present their solutions: 10:40 - 10:45 First solution provider, First company name (Country) 10:45 - 10:50 Second solution provider, Second company name (Country) 10:50 - 10:55 Third solution provider, Third company name (Country) 10:55 - 11:00 Forth solution provider, Forth company name (Country) 11:00 - 11:05 Fifth solution provider, Fifth company name (Country) When introducing the solution providers, the Moderator has to have some additional information regarding them: 1. First solution provider, First company name (Country). He has a lot of experience in implementing projects with immersive technologies. 2. Second solution provider, Second company name (Country). The team recently received a sponsorship award from Technorama, one of the main sponsors of the annual student solutions event in Lithuania. Today we have the opportunity to hear more about this solution. 3. Third solution provider, Third company name (Country). Artificial Intelligence-based solution, a spin-off company specialising in artificial intelligence. 4. Forth solution provider, Forth company name (Country). The presentation is part of a solution developed as part of a bachelor thesis and looks very promising. 5. Fifth solution provider, Fifth company name (Country). Company offers businesses and individuals the opportunity to build software 5x faster than most other companies. Representative of organizers uploads the order of participants to the chat. 11:05-11:20 ¦ Networking activities Moderator: thanks all the solution providers. Invites the Brando representative to reflect on what he heard, what stood out, if he has any questions for the presenters. Initiates a discussion among the participants. 11:20-11:30 ¦ Wrap-up Moderator: Thanks everyone for attending, reminds that those who did not share their contacts can still do so in the chat, that after the event we will share a joint email with information, wishes that the end of the event will mean the beginning of useful collaborations. |
| No 5. Example of the event link in LinkedIn | https://www.facebook.com/events/1134925417811739 |
| No 6. Example of the remainder e-mails to participant few days before the Event | Hello, This email is to remind you that you have registered to the event "Innovation Dialogues. How to co-create with corporations? ". The event takes place today, 3rd June, 2024. WHEN ¦ 10:00 – 11:30 EET WHERE ¦ Online via TEAMS 🔗Event link ¦ press HERE More about the event. See you soon! Kind regards, Organizing team |
| No 7. Example of the remainder e-mails to participant on the day of the Event | Hello, The event "Innovation Dialogues: How to co-create with corporations?" starts within 1 hour. WHEN ¦ 10:00 – 11:30 EET WHERE ¦ Online via TEAMS Event link ¦ Link to the event Please, join the webinar some minutes ahead of time and mute the microphone. More about the event. See you soon! Kind regards, Organizers |
| No 8. Example of the follow-up letter to participants and request to fill in the satisfaction survey | Dear Participants, We would like to thank you for participating in yesterday’s event Innovation Dialogues: How to co-create with corporations?. We hope that the contacts made will successfully transfer to future collaborations. We would appreciate it if you could take a moment ➡️to fill out a short survey to evaluate your experience at the event. Your feedback will help us improve and better respond to your needs in future events. 🔗Link to the survey: https://forms.office.com/e/FAS3wyfAwr Thank you once again for your participation! Best regards, The Organizers |